## PurchaseOrders
PurchaseOrderID | VendorID | ProjectID | MaterialCategory | MaterialName | OrderDate | DeliveryDate | Quantity | UnitCost | TotalCost | DeliveryStatus | DelayDays
PO001 | VEN001 | PRJ001 | Structural Steel | Steel Beams | 2023-03-15 | 2023-04-10 | 120 | 2100 | 252000 | Delivered | 5
PO002 | VEN002 | PRJ001 | Concrete | Ready-Mix Concrete | 2023-03-20 | 2023-04-18 | 500 | 420 | 210000 | Delivered | 0
PO003 | VEN003 | PRJ001 | Formwork | Timber Formwork Panels | 2023-04-01 | 2023-05-05 | 80 | 950 | 76000 | Delivered | 3
PO004 | VEN004 | PRJ002 | Electrical | Electrical Panels | 2023-07-01 | 2023-08-15 | 25 | 7200 | 180000 | Delivered | 0
PO005 | VEN005 | PRJ002 | Glazing | Curtain Wall Glass Units | 2023-07-10 | 2023-09-01 | 200 | 1800 | 360000 | Delivered | 8
PO006 | VEN006 | PRJ002 | HVAC | Air Handling Units | 2023-08-01 | 2023-09-20 | 10 | 22000 | 220000 | Delivered | 0
PO007 | VEN007 | PRJ003 | Finishing | Marble Floor Tiles | 2023-01-20 | 2023-03-01 | 3000 | 85 | 255000 | Delivered | 12
PO008 | VEN008 | PRJ003 | Electrical | Smart Lighting Systems | 2023-02-01 | 2023-03-15 | 150 | 3200 | 480000 | Delivered | 0
PO009 | VEN001 | PRJ003 | Structural Steel | Steel Columns | 2023-01-15 | 2023-02-28 | 60 | 3100 | 186000 | Delivered | 7
PO010 | VEN009 | PRJ004 | Concrete | Precast Concrete Slabs | 2023-09-10 | 2023-10-20 | 400 | 580 | 232000 | Delivered | 0
PO011 | VEN002 | PRJ004 | Structural Steel | Structural Steel Frames | 2023-09-15 | 2023-11-01 | 90 | 2400 | 216000 | In Transit | 4
PO012 | VEN010 | PRJ004 | Waterproofing | Membrane Waterproofing | 2023-10-01 | 2023-11-15 | 200 | 650 | 130000 | Pending | 0
PO013 | VEN003 | PRJ005 | Road Construction | Asphalt Mix | 2022-11-15 | 2023-01-10 | 1200 | 310 | 372000 | Delivered | 18
PO014 | VEN011 | PRJ005 | Road Construction | Road Kerbs & Drainage | 2022-12-01 | 2023-02-01 | 800 | 270 | 216000 | Delivered | 22
PO015 | VEN004 | PRJ005 | Electrical | Traffic Signal Systems | 2023-01-10 | 2023-03-20 | 30 | 14500 | 435000 | Delivered | 0
PO016 | VEN005 | PRJ006 | Finishing | Stadium Seating Units | 2023-07-10 | 2023-09-01 | 8000 | 320 | 2560000 | Delivered | 0
PO017 | VEN012 | PRJ006 | Finishing | Artificial Turf | 2023-07-15 | 2023-08-30 | 6000 | 95 | 570000 | Delivered | 6
PO018 | VEN006 | PRJ006 | MEP | Stadium HVAC Systems | 2023-08-01 | 2023-09-15 | 8 | 85000 | 680000 | Delivered | 0
PO019 | VEN007 | PRJ007 | Concrete | High-Strength Concrete | 2024-01-20 | 2024-03-01 | 800 | 470 | 376000 | Delivered | 0
PO020 | VEN013 | PRJ007 | Structural Steel | Industrial Steel Frames | 2024-02-01 | 2024-04-15 | 150 | 2800 | 420000 | In Transit | 9
PO021 | VEN008 | PRJ007 | MEP | Industrial Electrical Cabling | 2024-02-15 | 2024-04-01 | 500 | 980 | 490000 | Pending | 0
PO022 | VEN009 | PRJ008 | Finishing | Office Fit-Out Partitions | 2023-04-10 | 2023-06-01 | 300 | 750 | 225000 | Delivered | 14
PO023 | VEN001 | PRJ008 | Structural Steel | Steel Mezzanine Structures | 2023-04-15 | 2023-06-10 | 40 | 3800 | 152000 | Delivered | 0
PO024 | VEN010 | PRJ008 | Electrical | Low Voltage Systems | 2023-05-01 | 2023-07-01 | 1 | 185000 | 185000 | Delivered | 5
PO025 | VEN011 | PRJ009 | Marine | Precast Concrete Quay Walls | 2023-10-15 | 2024-01-20 | 600 | 1200 | 720000 | In Transit | 0
PO026 | VEN002 | PRJ009 | Structural Steel | Port Steel Gantry Frames | 2023-11-01 | 2024-02-15 | 25 | 48000 | 1200000 | Pending | 0
PO027 | VEN012 | PRJ009 | Marine | Piling Works Materials | 2023-10-20 | 2024-01-10 | 200 | 4200 | 840000 | In Transit | 11
PO028 | VEN013 | PRJ010 | Concrete | Concrete Blocks | 2024-02-10 | 2024-04-01 | 600 | 180 | 108000 | Delivered | 0
PO029 | VEN003 | PRJ010 | Finishing | External Cladding Panels | 2024-03-01 | 2024-05-15 | 1200 | 420 | 504000 | In Transit | 0
PO030 | VEN004 | PRJ010 | MEP | Plumbing Fixtures | 2024-03-15 | 2024-05-01 | 400 | 380 | 152000 | Pending | 0
PO031 | VEN014 | PRJ011 | Road Construction | Desert Road Base Course | 2023-09-01 | 2023-11-15 | 5000 | 280 | 1400000 | Delivered | 21
PO032 | VEN001 | PRJ011 | Structural Steel | Structural Steel Sections | 2023-09-15 | 2023-12-01 | 300 | 2600 | 780000 | Delivered | 9
PO033 | VEN015 | PRJ011 | MEP | Water Supply Pipeline | 2023-10-01 | 2024-01-01 | 2000 | 650 | 1300000 | In Transit | 0
PO034 | VEN005 | PRJ011 | Electrical | High Voltage Cables | 2023-11-01 | 2024-02-01 | 1000 | 1100 | 1100000 | Pending | 0
PO035 | VEN006 | PRJ012 | Road Construction | Asphalt Pavement Mix | 2023-05-10 | 2023-07-01 | 900 | 310 | 279000 | Delivered | 0
PO036 | VEN016 | PRJ012 | Road Construction | Road Signage & Markings | 2023-05-20 | 2023-07-10 | 1 | 95000 | 95000 | Delivered | 0
PO037 | VEN007 | PRJ013 | Structural Steel | Deep Foundation Steel Piles | 2024-03-10 | 2024-06-01 | 200 | 8500 | 1700000 | In Transit | 0
PO038 | VEN017 | PRJ013 | Concrete | Ultra-High Strength Concrete | 2024-03-15 | 2024-06-15 | 1000 | 890 | 890000 | Pending | 0
PO039 | VEN008 | PRJ013 | Waterproofing | Foundation Waterproofing System | 2024-04-01 | 2024-07-01 | 500 | 720 | 360000 | Pending | 0
PO040 | VEN009 | PRJ014 | Concrete | Concrete Ready Mix | 2024-01-10 | 2024-02-20 | 700 | 430 | 301000 | Delivered | 7
PO041 | VEN018 | PRJ014 | Finishing | Facade Cladding Stone | 2024-01-20 | 2024-03-15 | 2500 | 560 | 1400000 | In Transit | 15
PO042 | VEN010 | PRJ014 | MEP | HVAC Chillers | 2024-02-01 | 2024-04-01 | 4 | 68000 | 272000 | Pending | 0
PO043 | VEN011 | PRJ015 | MEP | Industrial Piping Systems | 2024-01-15 | 2024-03-01 | 800 | 870 | 696000 | Delivered | 0
PO044 | VEN019 | PRJ015 | Electrical | Control & Instrumentation Panels | 2024-01-20 | 2024-03-10 | 12 | 28000 | 336000 | Delivered | 0
PO045 | VEN012 | PRJ015 | Structural Steel | Equipment Support Steel | 2024-02-01 | 2024-03-20 | 45 | 3200 | 144000 | Delivered | 3